## Slide 1: Digital Banking
Transformation · Board Review

## Slide 2
The case for change
01
Market shifts, customer behavior and the cost of inaction
Current-state diagnostic
02
Where we stand against digital leaders and peers
Vision and ambition
03
Our 2028 north-star and target operating model
Strategy and roadmap
04
Five pillars, phased delivery and key initiatives
The financial case
05
Investment, value at stake and expected returns
Risk, governance and ask
06
What we need from the Board to proceed at pace
Agenda

## Slide 3: Executive summary
Banking is being redrawn by digital-native competitors, rising expectations and aging core systems. Standing still erodes share and returns.
This program modernizes our core, scales data and AI, and rebuilds the customer experience to protect and grow franchise value.
What we propose
A three-year, five-pillar program to become a digital-first bank, sequenced in waves so value is captured early and risk stays contained. Funded largely through reinvested efficiency gains and stage-gating.
Investment is front-loaded; returns compound from year three.
What it delivers
Lower cost-to-serve, higher digital sales, stronger retention, and a platform that lets us launch products in weeks, not quarters. A measurably better experience for customers and colleagues.
Resilient, cloud-based infrastructure that scales with demand.
What we ask
The ask
Approve a $480M, three-year investment with phased stage-gates. We project a 22% cost-to-serve reduction, $1.4B in cumulative value, and payback by year three. The Board's decision sets the pace at which we close the gap to digital leaders.
Approve the program and phase-one funding
Endorse the target operating model
Confirm governance and stage-gates
Mandate quarterly value tracking

## Slide 4: The Case for Change

## Slide 5: An inflection point
Three forces are converging: digital-native challengers, customers who expect instant service, and the rising cost of legacy systems.
What is changing
Customers now open accounts, borrow and pay from a phone. Branch traffic is falling while digital interactions climb. Challengers win on speed and experience, and are taking the most profitable relationships.
Incumbent economics still rest on scale and trust — both ours to defend if we act decisively.
The window is open but narrowing: the banks that move now set the standards customers will expect from everyone.
Doing nothing is itself a choice — one that quietly cedes growth, talent and relevance to faster rivals.
Our scale, balance sheet and customer trust are advantages challengers cannot easily replicate — if we modernize fast enough.
Why now
Cloud, AI and modern data platforms have matured to the point where transformation is achievable at acceptable risk and cost. Capabilities that were experimental five years ago are now proven at scale, and the tooling, talent and partners exist to deliver them. Waiting only raises the cost and shrinks the lead we can still build.

## Slide 6: The forces at work
73%
of customers now bank primarily on digital channels
+19pp
growth in digital sales share over three years
2.3x
faster product launches at digital-native banks
-40%
decline in branch transactions across the network.
$18B
in deposits at risk from challengers by 2028
11%
of annual revenue at risk if we do not modernize
Across every metric the direction is the same: value is migrating to digital, and faster than our current plans assume.
The question is no longer whether to transform, but how fast.

## Slide 7: Channel migration
By channel
Share of customer interactions by channel, 2016-2025
Chart: 
| 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025
Mobile | 18 | 24 | 31 | 38 | 45 | 52 | 58 | 63 | 67 | 70
Web | 30 | 31 | 32 | 32 | 31 | 30 | 29 | 28 | 27 | 26
Branch & Call | 52 | 45 | 37 | 30 | 24 | 18 | 13 | 9 | 6 | 4
Mobile and web now account for the large majority of interactions; branch and call-center volumes keep falling. The shift is structural, not cyclical, and still accelerating.

## Slide 8: Digital adoption
Active (M)
Active customers by channel, 2016-2025 (millions)
Chart: 
| 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025
Digital active | 3.1 | 3.6 | 4.2 | 4.9 | 5.6 | 6.4 | 7.1 | 7.8 | 8.4 | 9
Mobile active | 1.2 | 1.8 | 2.6 | 3.5 | 4.4 | 5.3 | 6.1 | 6.9 | 7.6 | 8.2
Branch active | 6.8 | 6.4 | 6 | 5.5 | 4.9 | 4.3 | 3.7 | 3.2 | 2.8 | 2.5
Digital and mobile usage has more than doubled while branch usage has fallen by a third. Mobile-active customers will overtake branch-active this year.
+13%
+24%
-11%
CAGR

## Slide 9: Rise of challengers
Challenger growth
Challenger customers vs. ours, and share of new accounts
Chart: 
| 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025
Challenger customers (M) | 2 | 4 | 7 | 12 | 19 | 28 | 39 | 52 | 66 | 80
Our digital customers (M) | 3.1 | 3.6 | 4.2 | 4.9 | 5.6 | 6.4 | 7.1 | 7.8 | 8.4 | 9
Challenger share new (%) | 8 | 12 | 17 | 23 | 30 | 37 | 44 | 50 | 55 | 59
Neobanks and fintechs have scaled from a niche to a mainstream choice, and now win a majority of new-to-bank accounts. They compete on experience and speed, rarely on price.
Challengers grew from roughly two million customers in 2016 to an estimated eighty million in 2025, while our digital base grew far more slowly.
Their advantage is not capital but operating model: cloud-native platforms, small empowered teams, and a relentless focus on the customer journey. We hold the trust and balance sheet; what we lack is their speed. This program is designed to close that gap without putting either at risk.
Why it matters
Challengers now capture close to six in ten new-to-bank accounts in our core segments, and the customers they win skew younger and more digitally active — precisely the relationships that drive lifetime value. Left unaddressed, this steadily erodes both our growth and the average quality of our book over time.

## Slide 10: The cost of inaction
Chart: 
| Deposit attrition | Margin erosion | Excess cost-to-serve | Forgone growth
Value at risk | 42 | 26 | 18 | 14
Deposit attrition as price-sensitive customers move to challengers
Margin erosion from competition on rate and fees
Excess cost-to-serve locked in by legacy systems and branches
Forgone growth from slow, costly product launches
Where value leaks away
What this means
The cost of inaction is not a one-off hit but a compounding annual drag on growth, margin and cost. Each year of delay makes the gap harder and more expensive to close.

## Slide 11: Current State

## Slide 12: Digital maturity vs. peers
Score 0-100
Where we lead, lag and trail digital leaders by capability
Chart: 
| Mobile | Onboard | Payments | Lending | Data/AI | Cloud | Open Bk | Service | Security | Personlz
Our bank | 52 | 48 | 60 | 40 | 35 | 30 | 38 | 55 | 62 | 33
Peer average | 58 | 55 | 64 | 50 | 45 | 42 | 48 | 60 | 68 | 45
Digital leaders | 85 | 82 | 88 | 80 | 78 | 80 | 82 | 86 | 90 | 84
Our bank | 52 | 48 | 60 | 40 | 35 | 30 | 38 | 55 | 62 | 33
Leaders | 85 | 82 | 88 | 80 | 78 | 80 | 82 | 86 | 90 | 84
GapBiggest gaps: data, cloud and lending
Our bank
Leaders

## Slide 13: Capability assessment
Capability | Today | Peers | Leaders
Target '28 |  |  | 
Customer experience |  |  | 
Data & analytics |  |  | 
Cloud & platform |  |  | 
Product & lending
Operating model
We rate at or below peers on most capabilities and well behind leaders on the ones that matter most for growth.
Read
A full ball is leading practice; an empty ball is a material gap. Most of our gaps are concentrated in data, platform and speed.
Target '28
Where we aim to be by 2028 — at or near leading practice on the capabilities that matter most.
Maturity

## Slide 14: Where customers feel the friction
Four moments where our experience falls short of expectations
Onboarding
Account opening takes days and often forces a branch visit. Drop-off is high, and the customers we lose are disproportionately the digitally active ones we most want to win.
Roughly a third of digital applications are abandoned before completion.
Everyday servicing
Routine requests still route to branches and call centers. Customers wait, colleagues are tied up on low-value work, and cost-to-serve stays stubbornly high.
Most service contacts could be resolved digitally with the right tools.
Borrowing
Lending decisions are slow and opaque. Manual underwriting and disconnected data mean customers wait while faster lenders win the business.
Decision times lag digital lenders by days, not hours.
Personalization
Offers are generic and poorly timed. Without unified data we cannot anticipate needs, so cross-sell and retention both underperform peers.
Limited use of data leaves clear cross-sell value on the table.

## Slide 15: The constraint beneath it all
Aging core
Our core banking and data estate was built for a branch era. It is reliable but rigid: changes are slow, costly and risky, and most engineering effort goes to keeping the lights on rather than building new value.
Every customer-facing ambition runs into the same legacy bottleneck.
Modernizing the core is the unlock for everything else in this plan.
of the technology budget is spent running and maintaining legacy
70%
to ship a simple product change, versus weeks at digital leaders
Months

## Slide 16: Benchmark: us vs. leaders
Score 0-100
Capability scores today across ten dimensions
Chart: 
| Mobile | Onboard | Payments | Lending | Data/AI | Cloud | Open Bk | Service | Security | Personlz
Our bank | 52 | 48 | 60 | 40 | 35 | 30 | 38 | 55 | 62 | 33
Peer average | 58 | 55 | 64 | 50 | 45 | 42 | 48 | 60 | 68 | 45
Digital leaders | 85 | 82 | 88 | 80 | 78 | 80 | 82 | 86 | 90 | 84
Sales %
Digital sales share over time vs. peers and leaders
Chart: 
| 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025
Our bank | 12 | 15 | 18 | 22 | 26 | 30 | 34 | 38 | 42 | 46
Peer average | 15 | 19 | 24 | 29 | 34 | 39 | 44 | 48 | 52 | 55
Digital leaders | 25 | 32 | 40 | 47 | 54 | 60 | 65 | 69 | 72 | 75

## Slide 17: Vision & Ambition

## Slide 18: Become a digital-first bank customers choose for speed, simplicity and trust — at a challenger's cost and an incumbent's scale.

## Slide 19: Our 2028 north-star
Digital sales
share
65%
of sales completed end-to-end on digital channels
Cost-to-serve
lower
-22%
reduction in blended cost-to-serve vs. baseline
Customer NPS
uplift
+18
improvement in relationship net promoter score
Active digital
monthly
12M
monthly active digital customers
Core on cloud
of core
80%
of core workloads on modern cloud platforms
Time-to-market
to change
Weeks
to launch or change products, down from months

## Slide 20: Where to play
Protect & grow
core deposits and primary relationships — defend the franchise with a markedly better everyday experience.
Scale digitally
in lending, payments and SME — where digital reach and faster decisions can win profitable new business.
Selectively partner
for non-core capabilities and niche segments, rather than building everything ourselves.
Exit or fix
sub-scale, high-cost propositions that neither differentiate nor earn their place.
Low
High
Strategic value
Low
High
Right to win
Four plays, prioritized by value and our right to win
Focus
We concentrate investment where strategic value and our right to win are both high — and are disciplined about what we choose not to do.
Sequence
Protect-and-grow moves come first because they fund the rest; scale plays follow as the new platform matures.
Discipline
A clear stop-doing list matters as much as the to-do list; capacity is the binding constraint, not ideas.
Optionality
We keep the freedom to partner or build as the market shifts, rather than locking in early bets.
High value, high right-to-win first

## Slide 21: Strategy

## Slide 22: Five strategic pillars
Experience
Rebuild the customer experience around journeys, not products — a single app, faster onboarding, and service that resolves in the channel of choice. This is where customers feel the change first and where retention is won or lost.
Data & AI
Unify data and scale AI across service, personalization and risk. Move from reporting to real-time decisions so we can anticipate needs, automate routine work, and price and protect more accurately at the moment of interaction.
Core & cloud
Modernize the core and migrate to cloud so teams can ship safely and often. This is the foundation that turns every other ambition from a multi-month project into a routine, low-risk release.
Operating model
Adopt an agile, product-led operating model: small empowered pods funded to outcomes, with clear ownership and the autonomy to move at the pace the market now demands of us.
People
Build the talent and culture to sustain it — hire and reskill in cloud, data and product so capability lives inside the bank rather than depending on external vendors over the long run.

## Slide 23: Pillar 1 — Customer experience
What we will do
Deliver one modern app for everyday banking, cut account opening to minutes, and let customers resolve most needs digitally — with seamless escalation to a person when it matters. Redesign the highest-volume journeys end to end so they are fast, simple and consistent across channels.
Experience is where customers first feel the change, and where loyalty is earned.
Why it matters
Experience, not price, is now the main reason customers choose and stay with a bank. A markedly better everyday experience protects our deposit base, lifts digital sales, and improves NPS — the leading indicator of future growth and lower attrition across the franchise.
It is also the most visible proof point that the transformation is real.
Key insight
The banks winning today did not just digitize existing processes — they redesigned the journeys around the customer. We will do the same, starting with the few journeys that drive the most volume, value and frustration, and scaling from there.
Onboarding in minutes, not days
Self-service for routine needs
One consistent app experience
Help from a person when it counts
Tracked via NPS

## Slide 24: Pillar 2 — Data & AI at scale
Value $M
Projected value from AI use-case families, 2026-2035
Chart: 
| 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035
Service automation | 10 | 25 | 45 | 70 | 100 | 135 | 175 | 220 | 270 | 325
Personalization | 5 | 15 | 30 | 50 | 75 | 105 | 140 | 180 | 225 | 275
Risk & fraud | 8 | 18 | 32 | 50 | 72 | 98 | 128 | 162 | 200 | 242
Value compounds as use cases move from pilot to production
$840M
cumulative value from data and AI by 2035
$325M
annual run-rate from service automation alone
60%
of service contacts deflected or assisted by AI
3x
6x
From pilots to production at scale

## Slide 25: Pillar 3 — Core & cloud
The approach
We modernize the core progressively rather than in a single high-risk replacement. New capabilities are built on a cloud-native platform and connected to the legacy core through APIs, so we can deliver customer value early while steadily migrating workloads behind the scenes. High-value, lower-risk domains move first; the most complex are sequenced later, once patterns, tooling and confidence are established. At each step we decommission legacy components to stop paying twice.
Why it matters
The core is the binding constraint on everything else. Until teams can ship safely and often, every customer-facing ambition stays slow and expensive. Cloud also turns large fixed technology costs into scalable, usage-based ones, improves resilience and security, and frees engineering effort from maintenance toward building new value. This is the least visible pillar to customers but the one that determines whether the rest of the plan is achievable at all.

## Slide 26: Pillar 4 — Operating model
Outcome-funded pods
Fund small, cross-functional teams to outcomes rather than projects, with the autonomy and accountability to deliver end to end.
Clear ownership
Each journey and platform has a single accountable owner with authority over budget, priorities and delivery — no more diffuse accountability.
Continuous delivery
Replace big-bang releases with frequent, low-risk ones, reprioritizing quarterly as we learn what creates value.
The operating model is what makes speed repeatable rather than a one-off heroic effort, and it is the hardest pillar to copy.

## Slide 27: Pillar 5 — Talent & culture
Building capability that lives inside the bank, not in vendors
Hire and reskill
Bring critical cloud, data, product and design skills in-house through targeted hiring and large-scale reskilling, so delivery capability is owned rather than rented and improves with every release we make.
Reducing vendor dependence also lowers long-run cost and risk.
New ways of working
Embed agile, product-led ways of working with real autonomy and clear accountability. Leaders set outcomes and remove blockers; teams decide how to deliver, learning and adjusting quarterly rather than annually.
Culture change is gradual but is the difference between lasting and temporary gains.
Leadership and incentives
Align leadership, incentives and metrics to the transformation so the behaviors we ask for are the ones we reward. Make value delivered, not activity, the measure of success at every level.
What gets measured and rewarded is what actually changes on the ground.

## Slide 28: Roadmap

## Slide 29: A phased, four-wave journey
We sequence the work into four waves so value is captured early, risk stays contained, and each stage funds the next.
Wave 1
Foundations
Stand up cloud platform and data foundation; form first pods.
Wave 2
Build
Modernize the core, launch the new app, and scale digital sales and self-service.
Wave 3
Scale
Roll out AI-driven service, personalization and straight-through processing across journeys.
Wave 4
Optimize
Decommission legacy, optimize cost-to-serve, and embed continuous delivery as standard.

## Slide 30: Wave 1 — foundation priorities
Stand up the cloud landing zone and CI/CD
Build the unified data foundation
Form the first outcome-funded pods
Ship visible customer quick wins
Platform & data foundationEstablish the cloud landing zone, security guardrails and delivery pipeline, and begin unifying customer data so later waves can build quickly and safely on a stable base.
First delivery podsStand up a small number of cross-functional pods on the highest-value journeys, proving the operating model on real work before scaling it across the bank.
Customer quick winsDeliver a few visible improvements early — faster onboarding and self-service for top requests — to build momentum, trust and evidence that the program works.
Funding & governanceRelease phase-one funding against a clear stage-gate, with value tracked from day one so the Board sees evidence before the next tranche is committed.
Wave 1
Outcomes
1
2
3
4
Wave 1 lays the foundations and proves the model; it is deliberately scoped to show value within the first year.
By end of Wave 1
Cloud platform and data foundation live
First pods delivering on real journeys
Early quick wins in market
Stage-gate 1 evidence pack for the Board

## Slide 31: Initiative portfolio
Initiative | Pillar | Wave | Value | Risk | Owner
New mobile app | Experience | 1-2 | High | Med | CXO
Digital onboarding | Experience | 1 | High | Low | CXO
Data foundation | Data & AI | 1-2 | High | Med | CDO
AI service | Data & AI | 2-3 | High | Med | CDO
Core modernization | Core & cloud | 2-4 | High | High | CTO
Cloud migration | Core & cloud | 1-3 | Med | Med | CTO
The portfolio is deliberately concentrated: a small number of high-value initiatives, each with a single accountable owner, sequenced so that the foundational platform and data work precedes the capabilities that depend on it.
Lower-value or higher-risk ideas are held back rather than diluting focus.

## Slide 32: Quick wins vs. strategic bets
Quick wins
— high value, low effort: digital onboarding, self-service for top requests. Do these first to build momentum.
Strategic bets
— high value, high effort: core modernization, AI at scale. Sequence carefully and stage-gate.
Fill-ins
— lower value, low effort: useful but not urgent; do opportunistically when capacity allows.
Reconsider
— lower value, high effort: defer or drop unless they become enablers for something larger.
Low
High
Effort
Low
High
Value
Sequence by value and effort, not by enthusiasm
Principle
We start with high-value quick wins to build momentum and fund the harder work, while protecting capacity for the strategic bets that create lasting advantage.
Cadence
The portfolio is rebalanced each quarter as value is proven and priorities shift.
Discipline
The lower-left and lower-right quadrants are where good programs lose focus; we are explicit about what we will not do.

## Slide 33: The Financial Case

## Slide 34: Investment by phase
Investment ($M)
Capex, opex and change cost by phase, $M
Chart: 
| Foundation | Build | Scale | Optimize | Run
Capex | 60 | 140 | 110 | 60 | 30
Opex | 30 | 70 | 80 | 70 | 55
Change & people | 20 | 60 | 55 | 40 | 25
Foundation
Run
Build
Scale
Optimize
Stand up cloud, data and delivery foundations; deliberately lean.
Peak spend: core modernization and the new app are built here.
Roll AI, personalization and digital sales out across journeys.
Decommission legacy and lock in run-rate efficiency gains.
Steady-state run cost as continuous delivery becomes the norm.
Spend is front-loaded by design; benefits follow as capabilities reach scale. Roughly $480M over three years, then run cost.
Peak phase

## Slide 35: Value at stake by lever
Annual value, $M
Run-rate annual value by lever once fully scaled, $M
Chart: 
| Cost-to-serve | Digital sales | Cross-sell | Fraud loss | Ops efficiency | Channel shift | Retention
Year 3 | 120 | 90 | 60 | 40 | 80 | 70 | 50
Year 5 | 210 | 180 | 120 | 75 | 140 | 120 | 95
Run-rate | 240 | 210 | 140 | 85 | 160 | 135 | 110
Run-rate ($M)
240
210
140
85
160
135
110
Value is broad-based rather than reliant on any single lever, which lowers execution risk and concentration. The largest sources are lower cost-to-serve and higher digital sales.

## Slide 36: Revenue uplift trajectory
Annual uplift ($M)
Incremental revenue by source, 2026-2035, $M
Chart: 
| 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035
Digital sales | 20 | 55 | 95 | 140 | 185 | 225 | 260 | 290 | 315 | 335
Cross-sell | 10 | 28 | 50 | 78 | 108 | 138 | 165 | 188 | 208 | 225
New products | 5 | 15 | 32 | 55 | 82 | 112 | 142 | 170 | 195 | 218
Digital sales
Higher conversion and reach as the new app and onboarding scale; the largest and earliest revenue source in the plan.
Cross-sell
Unified data and personalization lift products per customer, with value compounding as models mature in production.
New products
A faster platform lets us launch and iterate propositions in weeks, opening revenue that is simply out of reach today.

## Slide 37: Cost-to-serve reduction
$/customer
Blended, digital and branch cost-to-serve, 2026-2035
Chart: 
| 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035
Blended | 142 | 135 | 126 | 116 | 108 | 101 | 95 | 90 | 86 | 83
Digital | 48 | 44 | 40 | 37 | 34 | 32 | 30 | 29 | 28 | 27
Branch | 310 | 300 | 292 | 285 | 279 | 274 | 270 | 267 | 265 | 263
Blended
Digital
Branch
Mobile
Call center
$142
$48
$310
$38
$410
2026 cost ($)
2035 cost ($)
Change by 2035
$83
$27
$263
$21
$360
-42%
-44%
-15%
-45%
-12%
Why it falls
Cost falls as volume shifts to digital and automation reduces manual work.

## Slide 38: Cumulative cash flow & payback
Headline economics
Cumulative investment, benefit and net cash, $M
Chart: 
| 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035
Cum. investment | 90 | 210 | 320 | 410 | 470 | 505 | 525 | 540 | 550 | 555
Cum. benefit | 20 | 70 | 150 | 265 | 420 | 610 | 830 | 1075 | 1330 | 1600
Net cash flow | -70 | -140 | -170 | -145 | -50 | 105 | 305 | 535 | 780 | 1045
The shape of the case
Net cash turns positive in year three and grows steadily thereafter.
$480M
total investment over three years, then run cost
Yr 3
projected payback on the cumulative investment
$1.4B
cumulative net value created by 2030.
2.9x
return on investment by the end of the horizon
Investment is front-loaded while benefits compound, so the early years are cash-negative by design.
The case does not rely on heroic assumptions: it turns on disciplined delivery of a concentrated set of levers, each tracked in the P&L and reviewed at every stage-gate before further funding is released.

## Slide 39: P&L impact by year
Benefit $M
Annual investment, savings and revenue, $M
Chart: 
| 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035
Investment | 180 | 210 | 150 | 90 | 60 | 40 | 30 | 25 | 20 | 20
Savings | 30 | 90 | 160 | 230 | 300 | 360 | 410 | 450 | 480 | 500
Revenue | 20 | 60 | 120 | 190 | 270 | 350 | 420 | 480 | 530 | 570
Costs concentrate in years one and two; net benefit turns positive in year three and grows as savings compound. Figures exclude wider revenue upside, shown separately.
Lever | Yr 3 | Yr 5
Cost-to-serve | -18% | -22%
Digital sales | +34% | +65%
Servicing cost | -$120M | -$210M
Income uplift | +$180M | +$420M
Net benefit | +$60M | +$430M
FTE redeployed | 900 | 1,800
All figures are management estimates at the midpoint of the modeled range and are refined at each stage-gate.
Targets

## Slide 40: Return on investment overview
Cum. $M
Chart: 
| 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035
Cum. value | 50 | 150 | 320 | 560 | 870 | 1240 | 1660 | 2120 | 2610 | 3120
Cum. investment | 180 | 390 | 540 | 630 | 690 | 730 | 760 | 785 | 805 | 825
Net value | -130 | -240 | -220 | -70 | 180 | 510 | 900 | 1335 | 1805 | 2295
Cumulative value vs. cumulative investment, $M Value overtakes investment in year three.
By year five the program is projected to return roughly three dollars of value for every dollar invested, driven by lower cost-to-serve and higher digital sales.
Headline returns
Returns are weighted to the back half of the program as savings compound and the new platform reaches scale; the early years are investment-heavy by design and tightly stage-gated.
return on total program investment by year five
2.9x
cumulative value created over the program horizon
$1.4B

## Slide 41: Risk & Governance

## Slide 42: Key risks & mitigations
Risk
Impact
Likelihood
Mitigation
Core migration disrupts service or data integrity
High
Medium
Progressive migration, parallel running and rollback
Delivery slips as scope and complexity grow
High
Medium
Stage-gated funding, tight prioritization, fixed cadence
Benefits under-realized versus the business case
High
Medium
Tracked in the P&L, owned by the business, gated
Talent and capability gaps slow delivery
Medium
High
Targeted hiring, large-scale reskilling, selective expert partners
Change fatigue erodes adoption and morale
Medium
Medium
Phased rollout, quick wins, clear communication
Cyber & resilience exposure
Regulatory scrutiny
Vendor concentration
Cost overrun
Adoption shortfall
Security designed in and continuously tested
Early, transparent regulator engagement each gate
Multi-sourcing and in-house capability cut reliance
Stage-gates, central contingency, tight scope control
Designed-in usability; adoption tracked by journey

## Slide 43: Risk posture at a glance
Five risks we actively manage, with current status and trend
Risks are owned, rated and reviewed at every stage-gate; none are currently rated red, and the program will not advance funding while a critical risk is open.
Delivery risk | Technology risk | Benefits risk | People risk
Regulatory risk |  | Stable | Managed through stage-gated funding, fixed cadence and tight scope control; trend is stable as governance beds in.
Technology risk |  | Improving | Progressive migration and automated testing reduce exposure; risk falls as legacy is retired wave by wave.
Benefits risk |  | Stable | Benefits owned by the business and tracked in the P&L; reviewed at each gate before further funding is released.
People risk |  | Improving | Hiring and reskilling are ahead of plan; partner support de-risks the early waves while in-house capability builds.
Regulatory risk |  | Stable | Early, transparent engagement keeps regulators informed; no concerns raised on the approach to date.
1
2
3
4
5
Bottom line
The risk profile is consistent with a transformation of this scale and is actively managed rather than merely monitored. The single most important control is the stage-gate: it ensures we only fund the next phase once the prior one has proven both delivery and value, which caps downside at each step rather than at the end.

## Slide 44: Governance model
Board oversight
The Board approves funding at each stage-gate and reviews value, risk and delivery quarterly against the business case.
1
2
3
Steering committee
An executive steering group owns prioritization, resolves cross-pillar trade-offs, and is accountable for benefits realization.
Delivery pods
Empowered, cross-functional pods deliver to outcomes within clear guardrails, reporting progress and value transparently.

## Slide 45: Operating cadence
Plan
Set outcomes and priorities for the quarter against the business case and the value still to be captured.
Deliver
Pods ship frequently in short cycles, within security, risk and architecture guardrails set centrally.
Measure value
Measure
Track value in the P&L and delivery against plan, with transparent, shared metrics across the program.
Review
Review at the stage-gate; release the next tranche of funding only when value and delivery targets are met.
Adapt
Reprioritize for the next quarter based on evidence, stopping or scaling initiatives as the data dictates.

## Slide 46: The Ask

## Slide 47: Critical success factors
Exec ownership
A named, accountable executive owner for each pillar, with real authority over budget, priorities and delivery.
Talent & skills
Hire and reskill in cloud, data and product so delivery capability lives inside the bank, not in vendors.
Modern platform
Cloud and API foundations that let teams ship safely and frequently from the very first wave onward.
Agile delivery
Cross-functional pods funded to outcomes, not projects, with priorities reset every quarter on evidence.
Value discipline
Benefits tracked in the P&L, with stage-gates that release funding only when results are delivered.
Tracked against four headline KPIs:
90% On-time milestone delivery
65% Digital sales share, 2028
$1.4B Cumulative value created
22% Cost-to-serve reduction
<5 Open critical risks

## Slide 48: Are we ready to deliver?
Strong
Executive sponsorship and Board alignment
Yes
Largely funded from reinvested efficiency
Build
Talent and skills, ahead of plan and building.
Ready
Delivery model proven on early pods
Live
Regulators engaged early and supportive
Readiness is strong on sponsorship, funding and approach; the watch item is talent, where hiring and reskilling must keep pace.
On balance, we are ready to commit to Wave 1 with confidence.
The biggest risk to readiness is delay, not capability — momentum matters.

## Slide 49: What we ask the Board
Approve program
Endorse the three-year Digital Banking Transformation and its five-pillar strategy as set out today.
Release funding
Commit funding for Wave 1, with subsequent tranches released against stage-gates on evidence of value.
Endorse model
Back the move to an agile, product-led operating model and the governance that goes with it.
Track value
Require quarterly reporting of value, risk and delivery against the business case, owned by the business.

## Slide 50: The next 90 days
On approval, we move immediately into mobilization, with clear owners and milestones for the first quarter.
01
02
03
Mobilize the program
Confirm pillar owners, stand up governance, and release Wave 1 funding against an agreed stage-gate plan.
Lay the foundations
Begin the cloud landing zone and data foundation, and form the first cross-functional delivery pods.
Ship the first quick wins
Start the highest-value journeys so customers and the Board see tangible progress within the first quarter.

## Slide 51: Governance milestones
2026
2027
2028
Foundation
Program launch, Wave 1 funding release, and the first stage-gate review by mid-year.
Acceleration
Core migration milestone and a mid-program value checkpoint with the Board.
Realization
Legacy retired, with full run-rate benefits confirmed and independently reviewed.
Each milestone is a formal stage-gate: funding for the next phase is released only when the prior phase has met its value and delivery targets.

## Slide 52: Key takeaways
The case for change is urgent and the window to act is open but narrowing as challengers scale and customer expectations rise.
      We have a clear, sequenced plan.
Five pillars, delivered in four waves, with value captured early.
  The financial case is compelling and disciplined, not speculative.
Payback by year three; roughly $1.4B of cumulative value.
  Investment is largely reinvested efficiency, released by stage-gate.
Risk is real but actively managed, gate by gate.
  Stage-gates cap downside; no critical risks are currently red.
      We are ready to start, and delay is the biggest risk we face.
Momentum and early wins matter as much as the destination.
  The decision today sets the pace at which we close the gap.
What we ask of the Board
  Approve the program, release Wave 1 funding, and mandate quarterly value tracking.
This is how a trusted, at-scale bank becomes a digital-first one — without betting the franchise to get there.
The choice is the pace of change, not whether to change at all.