## Slide 1: Automation Strategy 2026-2028
Ops & Delivery

## Slide 2: Agenda 2026
1
2
3
4
5
Topics
Time
Context
Current state: manual effort, costand pain points
Vision
Targets, pillars, and operating principles
Pipeline
Opportunity scan and prioritization approach
Platform
Tooling, architecture, and vendor direction
Roadmap
Phases, plans, and delivery methodology
10 min
15 min
15 min
15 min
20 min
Operate
CoE model, governance, and skills uplift
Value
Benefits, ROI, risks, and next steps
15 min
10 min
6
7

## Slide 3: Executive Summary
Today
  Our teams spend roughly 120,000 hours a year on repetitive, rule-based work across finance, HR, and operations.
  Manual handoffs drive a 4.2-day average cycle time on core processes and most rework traces back to data re-entry.
  Twelve bots exist today, built ad hoc by individual teams with no shared platform, standards, or support model.
  Tool licences are fragmented across departments, so we pay several vendors for overlapping capability.
  Demand for automation help already exceeds what local teams can deliver on their own.
The plan
  Stand up a shared automation platform and Centre of Excellence in H2 2026, funded centrally for three years.
  Deliver three waves of automations, starting with finance quick wins and scaling to AI-assisted document work.
  Target $5M in cumulative net benefit and 60% adoption across eligible processes by the end of FY2028.
  Upskill 200+ colleagues through a citizen-developer and champions programme rather than relying on contractors.
  Govern through a single intake, prioritization, and benefits-tracking process owned by the CoE.

## Slide 4: Today
of repetitive, rule-based work performed manually every year
120k hrs
core systems touched by manual re-keying and swivel-chair work
38 systems
average cycle time on core finance and HR processes
4.2 days
estimated annual cost of manual effort and error rework
$4.1M
bots already running, built ad hoc with no shared platform
12 bots
of staff say repetitive tasks crowd out higher-value work
61%

## Slide 5: Automation SWOT
Strengths
  Strong process documentation in finance and shared services
  Twelve working bots prove the concept and appetite internally
  Engaged ops leaders willing to sponsor and co-fund delivery
  Stable core systems with usable APIs in most domains
S
W
T
Opportunities
  120k hours of repetitive work is addressable in three waves
  AI document processing unlocks semi-structured work
  Shared platform consolidates overlapping tool spend
  Citizen-developer talent already exists in the business
Weakness
  No shared platform, standards, or support model for bots
  Automation skills concentrated in a handful of people
  No benefits tracking, so value today is anecdotal
  Fragmented licences and duplicated vendor spend
Threats
  Unmanaged bot sprawl creates security and audit exposure
  Key-person risk: ad hoc bots break when builders leave
  Change fatigue if early waves disrupt teams without value
  Doing nothing: manual cost grows with volume every year
O
Where we stand today

## Slide 6: Where Effort Goes Today
Chart: 
| Data entry | Reporting | Reconciliation | Approvals | Other
Share of hours | 34 | 26 | 18 | 14 | 8
Share of the 120k annual manual hours
Top categories by hours and cost
Five categories account for nearly all manual effort. Data entry and reporting alone consume six in ten manual hours.
Data entry
41k h
34%
Reporting
31k h
26%
Reconciliation
22k h
18%
Approvals
17k h
14%
>

## Slide 7: The Cost Of Standing Still
Chart: 
| 2023 | 2024 | 2025 | 2026
Labor cost ($M) | 3.2 | 3.6 | 4.1 | 4.6
Error rework ($M) | 0.8 | 1 | 1.2 | 1.5
Opportunity cost ($M) | 1.1 | 1.4 | 1.8 | 2.2
      Cost of manual work, 2023-2026 ($M)
Labor tied up in repetitive tasks has grown ~12% a year as volumes rise faster than headcount.
Error rework and opportunity cost compound the bill: every manual handoff adds delay and defects.
      What this means for us
On the current path, manual work costs us over $8M a year by 2026 across labor, rework, and lost capacity.
Volume growth is outpacing hiring, so the gap gets worse, not better, without automation.
The categories growing fastest, data entry and reporting, are also the easiest to automate.
Acting now lets Wave 1 savings fund the later, more advanced waves of the programme.
>

## Slide 8: Automation Vision

## Slide 9
Automate the routine, elevate the people: free our teams for judgment, quality, and care.

## Slide 10: Three North-Star Targets, FY28
60%
$5M
100k
Adoption
Sixty percent of eligible processes run with automation in the flow of work by the end of FY2028, measured quarterly by the CoE.
Value
Five million dollars in cumulative net benefit by FY2028, counting hard savings, capacity released, and error reduction, net of all platform and delivery costs.
Hours
One hundred thousand manual hours returned to teams each year, redeployed to customer-facing and analytical work rather than cut.

## Slide 11: Three Strategy Pillars
People
Champions in every department, a citizen-developer pathway, and a small expert CoE so capability lives in the business, not in contractors.
1
2
3
Process
One intake funnel, standard delivery method, and benefits tracking, so every automation is prioritized, built, and measured the same way.
Platform
A shared, secure automation platform: orchestration, RPA, AI document services, and integrations, run as a product with a roadmap.

## Slide 12: Four Operating Principles
Fix and simplify the process before automating it; we will not pave the cow path or automate waste.
Standardize
Build on the shared platform with reusable components, so the second automation is always cheaper than the first.
Automate
Instrument everything: every bot reports hours saved, errors avoided, and uptime to a single benefits dashboard.
Measure
Review, tune, and retire automations continuously; the portfolio is managed like a product, not a project.
Improve
4
Tenets

## Slide 13: The KPIs We Will Manage To
Four numbers tell us whether the strategy is working
60%
adoption
$5M
value
Share of eligible processes with automation live in production, reported quarterly by department.
Cumulative net benefit, validated by Finance against the benefits register, not self-reported.
9 mo
payback
96%
uptime
Average payback period per automation; anything over 18 months needs steering board sign-off.
Bot availability in business hours, with incidents handled through standard IT support.

## Slide 14: Savings Trajectory To FY2029
Value ($M)
Chart: 
| FY26 | FY27 | FY28 | FY29
Gross savings ($M) | 1.2 | 2.6 | 4.1 | 5
Run cost ($M) | 0.6 | 0.9 | 1.1 | 1.2
Net benefit ($M) | 0.6 | 1.7 | 3 | 3.8
$5M
cumulative net benefit by FY2028, growing to $3.8M annual net in FY2029
By FY2028
What the chart shows
18 mo
from start to break-even; Wave 1 wins fund later waves
Break-even
$1.2M
steady-state annual run cost for platform, licences, and CoE team
Run Cost
>

## Slide 15: Automation Fit By Department
Process | Finance | HR | IT | Sales | Ops | Supply | Legal | CS
Invoice handling | H | L | L | H | H | L | M | L
Onboarding | M | H | L | L | H | H | H | M
Reporting | M | H | M | M | H | H | H | L
Purchase orders | L | H | L | L | H | H | H | L
Case handling | L | L | L | M | M | L | H | H
High
Medium
Low
Fit by department
Fit combines manual hours, error rates, and rule clarity from the Q1 2026 process scan.
What stands out
Invoice work scores high in Finance, Sales, and Ops, so one payables pattern serves three teams.
One pattern
Onboarding, reporting, and purchase orders all run hot in Ops and Supply, the Wave 2 focus.
Wave 2 core
Case handling fits best in Legal and Customer Service, the natural home for AI triage in Wave 3.
AI, Wave 3

## Slide 16: Priority: Value vs Effort
Value vs payback by case
Low
High
Low
High
Payback
Value
Hours
Top-right quick wins, invoices, reporting, and reconciliation, anchor Wave 1 with fast payback.
High-value, slower cases like claims and onboarding wait for the platform and AI services.
Key Highlights
>
Claims
Onboard
Surveys
Tickets
Audits
Reports
Recon
Invoices
Orders

## Slide 17: Pipeline By Function
By function
Chart: 
| Finance | HR | IT Ops | Sales
Identified | 34 | 22 | 18 | 24
Qualified | 21 | 14 | 12 | 15
In build | 8 | 5 | 6 | 7
The scan surfaced 98 candidate automations. Finance leads on identified hours, but every function has qualified opportunities ready for Wave 1 and Wave 2 sequencing.
Function | Ideas | Hours | Value
Finance | 34 | 46k | $1.6M
HR | 22 | 24k | $0.8M
IT Ops | 18 | 21k | $0.7M
Sales | 24 | 29k | $1.0M
Total | 98 | 120k | $4.1M
Pipeline
Key Highlight
Hours and value are annualized and validated with process owners; the chart shows how candidates move from identified to qualified to build-ready in each function.

## Slide 18: Three Waves, Sequenced By Risk
Quick wins in core finance and reporting tasks
Scaling proven patterns onto one shared platform across departments
AI-assisted automation of document work
3
1
2
Ships in 2026, low risk, fast payback
to fund later waves
Wave 3: 2028 - AI document work
Wave 1: H2 2026 - 12 automations
Wave 2: 2027 - platform scale-out
  Document extraction, case triage, and assisted decisions, once data readiness and model governance are in place.
  Reusable components, citizen-developer studio, and rollout to HR, sales, and supply chain on the shared platform.
  Invoice handling, reconciliations, and standard reports: proven patterns, clear rules, and owners who are ready to go now.
Wave 2 builds the platform and CoE muscle for scaled delivery
Each Wave Funds And De-risks The Next
AI use cases require model risk review with compliance
High
Low
Expected payback and feasibility

## Slide 19: Intake To Production
Ideas captured (120)
Everything goes into one funnel: staff ideas, the process scan, and leadership asks.
Pipeline position as of June 2026
01
02
03
04
05
Assessed (74)
Qualified (38)
In build (16)
Live (22)
CoE analysts size effort, value, and risk within ten working days of submission.
Qualified cases get a validated business case and a wave assignment.
Build squads deliver on the shared platform using the standard method.
Live automations report benefits monthly to the value dashboard.

## Slide 20: Wave 1 Impact On Workload
Chart: 
| Q1 | Q2 | Q3 | Q4
Finance (k hrs) | 6 | 9 | 13 | 18
HR (k hrs) | 3 | 5 | 8 | 11
Operations (k hrs) | 4 | 7 | 11 | 15
      Hours saved per quarter (000s)
      Workload mix on target processes (%)
Chart: 
| Q1 | Q2 | Q3 | Q4
Manual (%) | 81 | 68 | 55 | 44
Automated (%) | 11 | 21 | 31 | 40
Assisted (%) | 8 | 11 | 14 | 16
Finance leads as invoice and reconciliation bots land first; HR and operations follow from Q2.
By Q4, Wave 1 alone returns 44,000 hours a quarter across the three functions.
The share of fully manual work on target processes drops from 81% to 44% within the year.
Assisted work grows too: people stay in the loop where judgment is needed.

## Slide 21: Top Wave 1 Candidates
Process | Owner | Effort | Why now
Invoices | Finance | 18,000 hrs/yr | Highest single source of manual hours; clear rules and a proven RPA pattern from the pilot.
Recons | Finance | 11,000 hrs/yr | Month-end pain for two teams; same data sources as invoicing, so components are reused.
Reports | Operations | 9,500 hrs/yr | Five departments want it; one standard reporting pattern covers most variants.
Onboarding | HR | 6,000 hrs/yr | Cuts new-hire setup from five days to one and removes 14 manual handoffs.
Access req | IT Ops | 4,800 hrs/yr | Standard access requests auto-fulfilled with full audit trail; reduces ticket backlog.
Why these five
Together these five automations cover 49,300 hours a year, about 40% of the addressable total.
Each has a named owner, validated rules, and payback inside nine months.
All five run on patterns the pilot already proved, so delivery risk in Wave 1 stays low.
Savings from this set fund the platform build-out and the Wave 2 scale-up.
Insight

## Slide 22: Three Tool Families
RPA + Workflow
Robotic process automation and workflow tooling for rule-based work.
Attended and unattended bots handle re-keying, reconciliations, and report runs end to end.
A low-code studio lets trained citizen developers build simple flows safely.
Carries most of Wave 1 and Wave 2 delivery.
AI + Doc Svcs
AI and machine-learning services for semi-structured work.
Document extraction, classification, and case triage with a human in the loop for exceptions.
All models pass model-risk review with compliance before production.
Unlocks Wave 3 document-heavy use cases.
Integration
APIs, events, and an iPaaS layer connecting our 38 core systems.
Prefer APIs over screen-scraping wherever they exist, so automations survive UI changes.
Reusable connectors cut build time on every later automation.
The quiet backbone of everything we ship.

## Slide 23: Target Platform Architecture
Orchestration layer, one control room schedules, monitors, and audits every automation we run.
Bot runtime and RPA, attended and unattended workers executing rule-based flows at scale.
AI document services, extraction, classification, and triage models with human review queues.
Integration and APIs, connectors and events linking the platform to our 38 core systems.
Monitoring and alerts, uptime, benefits, and incident telemetry feeding the value dashboard.
      Five building blocks support every automation we ship

## Slide 24: Capability Coverage By Tool Family
Attended + unattended |  |  |  | 
Prebuilt API connectors |  |  |  | 
Document extraction |  |  |  | 
Central audit logging |  |  |  | 
Low-code citizen studio |  |  |  | 
RPA suite
Scripts
iPaaS
AI docs
✓
✓
✓
✓
Capability coverage matrix
✓
✗
✓
✓
✓
✓
✗
✓
✓
✓
✓
✓
✗
✓
✓
✗

## Slide 25: Vendor Shortlist, Illustrative
Coverage
Ease of use
Cost
Support
Overall
Broad
Strong
$$$
Strong
Moderate
Strong
$$$
Moderate
Strong
Strong
$$
Broad
Moderate
Moderate
$$
Narrow
Strong
Limited
$
Strong
★★★★☆
★★★★☆
★★★★☆
★★★★☆
★★★★☆
Vendor
Vendor A
Vendor B
Vendor C
Vendor D
Vendor E
Scores are from the Q1 evaluation; final RFP in Q3

## Slide 26: Value Convergence
  RPA alone moves data; it is fast to ship but limited to fully rule-based tasks.
  AI alone reads and classifies, but needs workflow around it to act on anything.
RPA
  Analytics alone tells us where the pain is, but cannot remove it by itself.
  The overlap is the strategy: analytics finds the work, AI reads it, RPA executes it.
AI / ML
Analytics
  Wave 3 use cases sit deliberately in the intersection of all three capabilities.
      Three capabilities, strongest where they overlap

## Slide 27: Platform Readiness
Chart: 
| Gap | Ready
Platform | 28 | 72
Platform
Core platform stands at 72% ready: orchestration and RPA runtime are live, with the citizen studio landing in Q3.
Data readiness is 58%: document pipelines exist for finance, while HR and ops sources are still being connected.
Chart: 
| Gap | Ready
Security | 19 | 81
Chart: 
| Gap | Ready
Data | 42 | 58
Security review is 81% complete: access model and audit logging approved, with pen-test findings closing this quarter.
Data
Security

## Slide 28: Roadmap

## Slide 29: Four Phases To Scale
Q3 2026
Pilot
Stand up the platform, deliver the first five Wave 1 automations in finance, and prove the benefits-tracking loop end to end.
Q1 2027
Scale
Roll Wave 1 patterns across HR, operations, and sales; launch the citizen-developer studio and champions network.
Q2 2028
Optimize
Launch Wave 3 AI document services, retire low-value bots, and tune the portfolio against the $5M net benefit target.
Q3 2027
Embed
Move to product mode: standing squads, quarterly portfolio reviews, and automation embedded in process-design standards.

## Slide 30: Year-1 Monthly Plan With Milestones
Activities | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1. Intake |  |  |  |  |  |  |  |  |  |  |  | 
2. Assess |  |  |  |  |  |  |  |  |  |  |  | 
3. Design |  |  |  |  |  |  |  |  |  |  |  | 
4. Build |  |  |  |  |  |  |  |  |  |  |  | 
5. Test |  |  |  |  |  |  |  |  |  |  |  | 
6. Deploy |  |  |  |  |  |  |  |  |  |  |  | 
7. Train |  |  |  |  |  |  |  |  |  |  |  | 
8. Support |  |  |  |  |  |  |  |  |  |  |  | 
9. Measure |  |  |  |  |  |  |  |  |  |  |  | 
10. Scale |  |  |  |  |  |  |  |  |  |  |  | 
MVP
Go-live
Scale
2026
Platform MVP accepted
First five bots live
Twelve automations live

## Slide 31: FY2026 Workstream Plan
Platform
Finance
HR + Ops
CoE
Q2 2026
Q3 2026
Q1 2026
Q4 2026
Vendor selection
Env + security
Orchestrator live
Citizen studio
Process scan
Invoice bot build
Recon bots live
Reporting suite
Opportunity scan
Onboarding design
Onboarding live
Access requests
CoE hiring
Delivery method
Champions launch
Benefits dashbrd
Pen test fixes
DR runbook
Connector pack 1
Connector pack 2
UAT + hypercare
Month-end pilot
Scale to AP team
Audit handover
Job-aid library
HR data mapping
Ops case pilot
Wave 2 backlog
Intake launch
Training cohort 1
Training cohort 2
QBR cadence
Licence true-up
Monitoring live
Alert tuning
Perf hardening
Close FY plan
Sales scan
Supplier pilot
Benefits audit
Quarter by quarter, 2026

## Slide 32: How We Deliver Every Automation
CoE analysts qualify each idea with the process owner: effort, value, risk, and a signed benefits baseline before any build starts.
Ten working days, one page, one decision: build now, batch for later, or decline with reasons back to the requestor.
A squad designs and builds on the shared platform using standard components, with security and audit checks built into the pipeline.
Two-week sprints, demo every sprint to the process owner, and nothing ships without a tested rollback path.
Deploy with hypercare, hand over to standard support, and track benefits monthly against the baseline for at least a year.
Automations that stop earning their keep are tuned, repurposed, or retired at the quarterly portfolio review.
Discover and qualify
Design and build
Deploy and improve
>
>

## Slide 33: Intake-To-Deploy Pipeline
Intake One funnel for ideas from staff, scans, leaders | Assess Sized for effort, value, and risk in ten days | Build Standard squads, standard parts, shared platform | Deploy Hypercare, handover, and monthly benefits tracking
Requestor + champion | CoE analyst | Build squad | Ops + process owner
Idea record in portal | One-page business case | Tested automation | Live bot + benefits log
Any colleague | 10 working days | 4-8 weeks typical | 2 weeks hypercare
Stage detail
Who owns it
5 d
10 d
6 wk
2 wk
Typical duration
Owner
Output
Timing

## Slide 34: The CoE Operating Loop
Plan
Quarterly portfolio review sets wave priorities from the funnel, balancing value, risk, and team readiness.
Build
Squads deliver qualified automations on the shared platform using the standard method and reusable parts.
Run
Operations monitors uptime and incidents; every bot reports benefits to the value dashboard monthly.
Improve
Underperformers are tuned or retired; lessons feed standards, training, and the next quarter's plan.
The loop repeats every quarter
Owned end to end by the CoE
>
>
>
>
>
>
>

## Slide 35: Automation CoE Structure
CoE
Lead
Lead
Build
Lead
Platform
Lead
Quality
Lead
Change
Leads
  A core team of 12, with delivery squads drawing on trained citizen developers in the business. Reports to the COO.
Analyst
Triage
Analyst
Cases
Dev
RPA
Dev
RPA
Dev
AI/ML
Eng
Infra
Eng
Connect
Tester
UAT
Tester
Audit
Coach
Training
Coach
Champs
Comms
Adoption
Core team
Delivery
Enable

## Slide 36: Three Governance Forums
Automation Steering Board, monthly
CoE Delivery Review, weekly
Benefits Review with Finance, quarterly
  Sponsors from each function plus IT security and finance.
  Approves wave priorities and funding, resolves conflicts, and owns payback exceptions.
  CoE leads, squad leads, and the platform product owner.
  Tracks delivery against plan, unblocks squads, and reviews incidents from the prior week.
  Finance business partner, CoE lead, and process owners.
  Validates claimed benefits, signs off realized savings, and reports results upward.
Forum
Purpose

## Slide 37: Delivery RACI
Key handoffs to align on | Process owners (business teams) | CoE core team | Build squads | Platform/IT
Intake and prioritization | R | A | C | I
Solution design sign-off | A | C | R | C
Go-live approval | A | R | C | C
Benefits tracking | C | A | I | I
R = responsible, A = accountable, C = consulted

## Slide 38: Intake And Prioritization
      Every idea follows the same four steps, from any source to a decision
  Submit through the portal: a short form any colleague can complete in ten minutes, with a champion to help.
  CoE triage within five days: duplicates merged, quick clarifications handled directly with the requestor.
  Assessment in ten days: effort, value, and risk scored with the process owner; a benefits baseline is agreed.
  Decision at the next review: build now with a wave assignment, batch for later, or decline with reasons.
      What makes the funnel work in practice
Transparency: requestors see their idea's status at every step, and declined ideas always get reasons.
Speed: the clock from submission to decision is 20 working days or less, tracked as a CoE KPI.
Honesty: value scores are validated by finance, so the pipeline reflects real benefit, not enthusiasm.
1
2
3
4

## Slide 39: Operating Model: Why Hybrid
How it works
Strengths
Drawbacks
Centralized only: one expert team builds everything.
  A single central team owns intake, build, and run for every automation.
  Business teams submit requests and wait for central capacity.
  Consistent standards, security, and audit on every build.
  Bottleneck: the funnel already exceeds central capacity.
Federated only: each team builds its own, fast but fragmented.
  Every department picks tools and builds flows independently.
  No shared platform, standards, or central support model.
  High energy and ownership inside individual departments.
  Recreates today's sprawl, duplicate spend, and key-person risk.
Hybrid (chosen): a small expert CoE plus trained citizen developers.
  CoE owns the platform, standards, and complex builds end to end.
  Citizens build simple flows in the studio, inside guardrails.
  Scales delivery while keeping control, audit, and support.
  Needs sustained training investment and active guardrails.

## Slide 40: Pipeline Health View
Process | Dept | Stage | Owner | Go-live | Saving | RAG
Access requests | IT Ops | Assess | Squad 3 | Dec 2026 | $150k/yr | Red
Report suite | Ops | Design | Squad 2 | Oct 2026 | $300k/yr | Amber
Invoice handling | Finance | Build | Squad 1 | Aug 2026 | $520k/yr | Green
Onboarding | HR | Assess | Squad 2 | Nov 2026 | $190k/yr | Amber
Supplier portal | Supply | Assess | Squad 3 | Jan 2027 | $120k/yr | Red
Status as of June 2026
Watch items: access requests and the supplier portal are blocked on scope and vendor API access; both have named owners and July resolution dates.
Flagship on track: invoice go-live holds at August 2026.

## Slide 41: Three Enablement Streams
How we build capability
Role-based pathways from awareness to certified citizen developer.
Two champions per department carry demand, adoption, and feedback.
A monthly community of practice shares patterns and reusable parts.
Training
Champions
Community

## Slide 42: Skills Uplift Path
Everyone: a one-hour briefing on what automation is, what the programme will and will not change, and how to submit ideas to the funnel.
Volunteers: a two-day hands-on course in the citizen studio, building a real flow from their own team's backlog with CoE coaching.
Practitioners apply skills on the job: each graduate ships one supervised automation within 60 days of training, paired with a CoE developer.
Certification: an internal assessment of build quality, security practice, and documentation; certified builders work inside guardrails unsupervised.
Coaches: experienced certified builders mentor the next cohort and co-own the pattern library with the CoE, closing the loop.
Coach
Certify
Applied
Trained
Aware
5
4
3
2
1

## Slide 43: Ways Of Working: Before And After
Invoice data is keyed into three systems by hand; month-end means overtime and error-chasing across two teams.
Bots post invoices straight through; exceptions queue for human review and month-end closes two days earlier.
New starters wait up to five days for accounts and kit, chased through 14 manual handoffs by HR coordinators.
Onboarding triggers everything on day one automatically; HR time goes to welcoming people, not chasing tickets.
Reports are rebuilt by hand in spreadsheets every week, differently in every team, with no single source of truth.
Standard reports generate and distribute themselves; analysts spend their week on the why, not the what.
Before
After

## Slide 44: Enablement Rollout Status
Chart: 
| Category 1
Content | 55
Marketing | 20
Technology | 15
Other | 10
Awareness
55% of all staff have completed the one-hour briefing; remaining sessions are scheduled through September.
Trained 20% have finished the two-day citizen-developer course, ahead of the 15% plan for this point in the year.
Certified 15% have passed certification and can build unsupervised inside guardrails.
Champions Champion coverage stands at 10 of 12 departments; legal and supply chain nominate theirs this month.
Progress against FY2026 enablement targets

## Slide 45: Investment And Savings
Cumulative savings build slowly through the platform phase, then compound as each wave lands on shared components.
The program is self-funding from mid-2027: Wave 1 savings cover the run cost and most of Wave 2 delivery.
Key Highlights
Cumulative savings ($M), half-yearly
Chart: 
| H1 26 | H2 26 | H1 27 | H2 27 | H1 28 | H2 28
Cumulative savings ($M) | 0.3 | 0.9 | 1.8 | 3 | 4.4 | 6
$7.5M
invested over three years
$13.5M
gross savings by FY2028
9 mo
average payback per bot
180%
program ROI by FY2028
Validated by Finance against the benefits register

## Slide 46: Cost And Benefit Curves
Cost
Chart: 
| FY26 | FY27 | FY28 | FY29
Platform ($M) | 0.8 | 0.9 | 0.9 | 0.9
Delivery ($M) | 1.2 | 1.6 | 1.4 | 1.1
Change ($M) | 0.3 | 0.4 | 0.3 | 0.2
      Program cost by year ($M)
      Benefits realized by year ($M)
Chart: 
| FY26 | FY27 | FY28 | FY29
Hard savings ($M) | 0.6 | 1.8 | 3.2 | 4.4
Soft savings ($M) | 0.4 | 0.9 | 1.5 | 2
Risk avoided ($M) | 0.1 | 0.3 | 0.5 | 0.8
12%
18%
26%
31%
8%
15%
22%
29%
Costs peak in FY2027 during the Wave 2 scale-out, then fall as delivery shifts to citizen developers.
Benefits cross costs in mid-2027 and keep compounding as the portfolio grows and matures.
Benefit

## Slide 47: Program ROI Summary
Chart: 
| FY26 | FY27 | FY28 | FY29 | FY30 | FY31
Cumulative ROI (%) | 20 | 65 | 120 | 180 | 230 | 270
Cumulative program ROI (%)
>
180%
ROI by FY28
$13.5M
gross saved
9 mo
avg payback
$3.8M
net in FY29
Net of all platform, licence, and people costs

## Slide 48: Where The Benefits Come From
Chart: 
| Other | Counted
Hard savings | 38 | 62
Chart: 
| Other | Counted
Capacity | 56 | 44
Hard saves
62% of benefit is hard savings: licence consolidation, overtime reduction, and error-rework eliminated. These are cash-out numbers Finance signs off line by line, and they fund the program's run cost on their own. of total benefit
Capacity
44% of released hours are redeployed to customer-facing and analytical work. We count capacity as benefit only when the receiving manager confirms the hours landed on named higher-value activities. hours redeployed
Chart: 
| Other | Counted
Quality | 45 | 55
Quality
Error rates on automated processes drop by half or more, avoiding rework, penalties, and audit findings.
Mix

## Slide 49: Run-Rate Trends
Chart: 
| Q1 | Q2 | Q3 | Q4
FY26 actual (k hrs) | 8 | 14 | 21 | 30
FY27 plan (k hrs) | 34 | 38 | 43 | 48
Target (k hrs) | 10 | 18 | 28 | 40
Chart: 
| Q1 | Q2 | Q3 | Q4
Manual baseline | 6.2 | 6.1 | 6 | 6
Automated | 1.1 | 0.9 | 0.8 | 0.6
Blended | 4.8 | 4.2 | 3.5 | 2.8
      Hours saved per month (000s)
Monthly hours saved climb as each automation lands; FY2027 plan assumes Wave 2 patterns reuse Wave 1 components.
      Errors per 1,000 transactions
Error rates on automated processes fall steadily; manual baselines stay flat, which widens the quality gap every quarter.
Value dashboard data

## Slide 50: Next 90 Days
      Four Moves Between Now And September Set Up Wave 1 Delivery
  Close vendor selection and sign the platform contract by mid-July, with security review running in parallel, not after.
  Stand up the first two build squads and start the invoice and reconciliation builds the first week of August.
  Launch the intake portal and run the first champions cohort, so the funnel is filling while the squads build.
  Baseline benefits with Finance for every Wave 1 process, so go-live savings are measured, not estimated.
      What We Need From This Group Today
1
2
3
4
  Confirm the two squad staffing asks by Friday
  Nominate champions for the four open slots
  Agree the benefits baseline method with Finance
  Hold August calendars for go-live hypercare

## Slide 51: The Trajectory From Here
Twenty-seven automations live by mid-2027 is the gate for Wave 3 funding; we are tracking two ahead of that line today.
Every automation on the chart carries a validated benefits baseline, so the value claim grows with the count.
The slope matters more than any single quarter: shared components make each new automation cheaper than the last.
Key Highlights
Automations live in production
Chart: 
| Q1 26 | Q2 26 | Q3 26 | Q4 26 | Q1 27 | Q2 27
Automations in production | 2 | 5 | 9 | 14 | 20 | 27
27
live automations by mid-2027
96%
bot uptime in business hours
Counting only production bots on the platform

## Slide 52: What We Need From You
Send people, not just ideas: nominate one champion and two citizen-developer candidates per department by end of June, and protect their training time in Q3.
Nominate people
Bring your worst process to the funnel first: the intake portal opens July 1, and the best Wave 2 slots go to well-documented, owner-backed submissions.
Feed the funnel
Plan for the hours you get back: every team receiving automation agrees up front where released time goes, so the benefit lands on real work, not evaporates.
Plan the payback